# SAP Business One Contract Management Add-On

Document 3: Business Logic & Workflows

# 1. Contract Lifecycle Workflow

## 1.1 Contract States

Contracts progress through the following states:

| Status Code | Status Name | Description |
| --- | --- | --- |
| D | Draft | Initial creation, can be edited freely |
| A | Active | Approved and active, can create ICPs |
| H | On Hold | Temporarily suspended, no new ICPs allowed |
| C | Completed | Work finished, all payments processed |
| X | Cancelled | Contract terminated before completion |

## 1.2 State Transition Rules

- Draft → Active: Requires approval by authorized user

- Active → On Hold: Can be done by manager at any time

- On Hold → Active: Requires reason and approval

- Active → Completed: Only when all work is done and final payment made

- Any State → Cancelled: Requires high-level approval and cancellation reason

- Completed/Cancelled: Cannot be changed back to other states

# 2. ICP Processing Workflow

## 2.1 ICP States

| Status Code | Status Name | Description |
| --- | --- | --- |
| D | Draft | Being prepared, calculations in progress |
| S | Submitted | Submitted for approval, awaiting review |
| A | Approved | Approved, ready to generate invoice |
| P | Paid | Invoice generated and payment received |
| R | Rejected | Rejected by approver, needs revision |

## 2.2 ICP Calculation Logic

The ICP calculation follows this sequence:

- Calculate Gross Value: Sum of (This Period Qty × Unit Price) for all lines

- Deduct Advance Payment: Subtract any advance payment deduction

- Calculate Retention: Multiply remaining amount by retention percentage

- Deduct Retention: Subtract retention amount

- Deduct Materials: Subtract material deduction if applicable

- Deduct Other: Subtract any other deductions

- Calculate VAT: Apply tax rate to subtotal after all deductions

- Net Payment: Subtotal after deductions + VAT amount

## 2.3 Cumulative Value Tracking

- System tracks cumulative quantities for each contract line item

- Previous Qty = Sum of all previous ICP quantities for this line

- Cumulative Qty = Previous Qty + This Period Qty

- Completion % = (Cumulative Qty / Contract Qty) × 100

- System prevents exceeding 100% completion

# 3. Approval Workflows

## 3.1 Contract Approval

- User creates contract in Draft status

- User submits for approval, status remains Draft, ApprovalStatus = Pending

- Approver reviews contract details and financial impact

- If approved: Status = Active, ApprovalStatus = Approved

- If rejected: Status = Draft, ApprovalStatus = Rejected (user can revise and resubmit)

- System logs all approval actions in workflow history

## 3.2 ICP Approval

- Project engineer creates ICP in Draft status

- System calculates all values automatically

- Engineer submits ICP, status = Submitted

- Project manager reviews work completion and values

- If approved: Status = Approved, system auto-generates AR Invoice

- If rejected: Status = Rejected, engineer revises and resubmits

- Once invoice is paid: Status = Paid

# 4. Financial Integration Logic

## 4.1 AR Invoice Generation

When ICP is approved, system automatically creates AR Invoice:

- Customer: From ICP U_CardCode

- Document Date: ICP U_CertDate

- Payment Terms: From Business Partner master data

- Currency: From contract

- Invoice Lines: One line per ICP line item with this period value

- Deductions: Added as negative lines or separate deduction lines

- Tax: Applied according to contract tax code

- Reference: ICP number stored in user field

## 4.2 Retention Management

- Retention amount is calculated but not invoiced

- System tracks cumulative retention in RVCM_RETEN table

- When contract is completed, retention can be released

- Release creates a separate AR Invoice for retained amounts

- Partial releases supported with approval

## 4.3 Payment Tracking

- System links ICPs to AR Invoices (U_InvoiceEntry)

- When payment is received, status updates to Paid

- Payment Schedule (RVCM_PYMSCH) tracks milestone payments

- Dashboard shows payment status and outstanding balances

# 5. Amendment Processing

## 5.1 Contract Amendment Workflow

- User creates amendment record (RVCM_AMEND)

- Specifies reason, value change, and/or time extension

- Amendment requires approval before taking effect

- Upon approval, system updates contract values/dates

- Original values preserved in amendment history

- Amendment impacts all future ICPs automatically

# 6. Business Rules

## 6.1 Critical Business Rules

- Cannot delete contract with approved ICPs

- Cannot create ICP for non-Active contract

- Cannot exceed 100% completion on any line item

- Cumulative payment cannot exceed contract total value

- Must have at least one approved ICP before marking contract Completed

- Retention release requires completion of contract or specific milestone

- All amounts must be in contract currency

=== END OF DOCUMENT 3 ===

Business Logic & Workflows