SAP Business One

Contract Management Add-On

Document 5: Implementation Guide

Version 1.0

11/12/2025

# Executive Summary

This document provides a comprehensive implementation guide for the SAP Business One Contract Management Add-On, including development roadmap, deployment procedures, testing strategies, and go-live checklist.

# 1. Implementation Roadmap

## 1.1 Project Timeline Overview

| Phase | Duration | Effort | Deliverable |
| --- | --- | --- | --- |
| Phase 1: Database Setup | Week 1-2 | 80 hours | All UDTs/UDFs created |
| Phase 2: UI Development | Week 3-5 | 120 hours | Contract & IPC forms |
| Phase 3: Business Logic | Week 6-8 | 120 hours | Workflows & calculations |
| Phase 4: Integration | Week 9-10 | 80 hours | DI API & Service Layer |
| Phase 5: Testing & UAT | Week 11-12 | 80 hours | Production-ready system |

## 1.2 Phase 1: Database Setup (Weeks 1-2)

### Week 1: Core Tables

- Create @CNTR_HEADER UDT with all 16 fields

- Create @CNTR_LINES UDT with all 13 fields

- Create @CNTR_PAYMENT UDT with all 10 fields

- Add primary keys and indexes for performance

- Test insert/update/delete operations

### Week 2: IPC Tables & Supporting Tables

- Create @CNTR_IPC_HDR UDT with all 15 fields

- Create @CNTR_IPC_LINES UDT with all 12 fields

- Create @CNTR_APPROVALS, @CNTR_DOCUMENTS, @CNTR_TERMS tables

- Create stored procedures for number series generation

- Load test data for validation

### Critical Success Criteria

- All UDTs created without errors in SAP B1

- Foreign key relationships validated

- Index performance tested with 10,000+ records

- Backup and restore procedures documented

## 1.3 Phase 2: UI Development (Weeks 3-5)

### Week 3: Contract Master Form

- Create Contract form with 3 tabs (General, Lines, Documents)

- Implement toolbar buttons (Add, Update, Cancel, Find, Approve)

- Add all General tab fields with proper data bindings

- Implement auto-fill logic for Customer selection

- Test bilingual support (English/Arabic) with RTL layout

### Week 4: Contract Lines Matrix

- Create matrix grid for contract line items

- Add columns: Item, Description, Quantity, Unit Price, Discount, Tax, Total

- Implement real-time calculation logic

- Add row-level validation

- Test add/delete/edit row operations

### Week 5: IPC Form Development

- Create IPC form with header and lines sections

- Implement Contract lookup with auto-fill

- Add IPC calculation fields (Retention, Advance Deduction, Net Payable)

- Create IPC lines matrix with work completion %

- Test all calculation formulas with sample data

### Critical Success Criteria

- Forms fully functional in both English and Arabic

- All field validations working correctly

- Real-time calculations accurate to 4 decimal places

- Keyboard navigation fully operational

# 2. Deployment Procedures

## 2.1 Pre-Deployment Checklist

| Item | Description | Status |
| --- | --- | --- |
| 1 | Full database backup completed | ☐ |
| 2 | All UDTs tested in development environment | ☐ |
| 3 | User permissions configured | ☐ |
| 4 | Add-on compiled and signed | ☐ |
| 5 | User training materials prepared | ☐ |
| 6 | Rollback plan documented | ☐ |
| 7 | Support team briefed | ☐ |

# 3. Testing Strategy

## 3.1 Unit Testing

- Test each stored procedure independently

- Verify all calculation formulas with known test cases

- Test field validation rules

- Verify date range validations

## 3.2 Integration Testing

- Test Contract to IPC workflow end-to-end

- Test IPC to A/R Invoice generation

- Verify approval workflow transitions

- Test data synchronization between tables

## 3.3 User Acceptance Testing (UAT)

- Create 10-15 real-world test scenarios

- Have end users perform daily operations

- Document all user feedback and issues

- Retest after bug fixes

## 3.4 Performance Testing

- Load test with 10,000+ contracts

- Test IPC generation performance

- Verify report generation speed

- Test concurrent user access

# 4. Go-Live Checklist

| Day | Activity | Owner |
| --- | --- | --- |
| D-7 | Final UAT sign-off received | PM |
| D-5 | Production database backup completed | DBA |
| D-3 | User training sessions completed | Trainer |
| D-1 | Deploy add-on to production | Dev Team |
| D-1 | Verify all UDTs and forms accessible | QA Team |
| D-Day | Go-Live! | All |
| D+1 | Post-deployment review meeting | PM |

# 5. Post-Go-Live Support

## 5.1 Hyper-Care Period (First 30 Days)

- Daily check-ins with key users

- 24/7 support hotline available

- Monitor system performance metrics

- Rapid bug fix deployment process

## 5.2 Ongoing Maintenance

- Monthly system health checks

- Quarterly feature enhancement reviews

- Annual SAP B1 version compatibility testing

- Regular database optimization

## 5.3 Knowledge Transfer

- Technical documentation handover to IT team

- User guide distribution to all end users

- Administrator training for system configuration

- Troubleshooting guide for common issues

# 6. Success Metrics & KPIs

| KPI | Target | Measurement |
| --- | --- | --- |
| User Adoption Rate | > 90% | Active users / Total users |
| System Uptime | > 99.5% | Monthly uptime % |
| Contract Processing Time | < 30 min | Avg time from draft to active |
| IPC Generation Time | < 5 min | Avg time to create IPC |
| Calculation Accuracy | 100% | Zero calculation errors |
| User Satisfaction | > 4.0/5.0 | Monthly user surveys |

End of Implementation Guide

Ready for Project Execution