SAP Business One

Contract Management Add-On

Document 6: IPC Module Specifications

Version 1.0

11/12/2025

# 1. IPC Module Overview

## 1.1 Purpose

The Interim Payment Certificate (IPC) module manages progressive payment requests based on work completion. It is essential for construction, engineering, and project-based contracts where payments are made in stages rather than lump sum.

## 1.2 Key Features

- Progressive payment tracking based on work completion percentage

- Automatic retention calculation and tracking

- Advance payment deduction management

- Multi-stage approval workflow

- Automatic A/R Invoice generation upon approval

- Historical IPC tracking per contract

# 2. Database Schema

## 2.1 @CNTR_IPC_HDR (IPC Header Table)

| Field | Type | Size | Required | Description |
| --- | --- | --- | --- | --- |
| Code | nvarchar | 20 | Yes | Primary Key, IPC Number |
| U_ContractNo | nvarchar | 20 | Yes | FK to @CNTR_HEADER |
| U_CustomerCode | nvarchar | 15 | Yes | FK to OCRD |
| U_IPCDate | date | - | Yes | IPC issuance date |
| U_PeriodFrom | date | - | No | Work period start |
| U_PeriodTo | date | - | No | Work period end |
| U_Status | nvarchar | 20 | Yes | Draft/Submitted/Approved/Rejected/Paid |
| U_RetentionPct | decimal | 19,6 | Yes | Retention percentage (0-100) |
| U_AdvDeductPct | decimal | 19,6 | No | Advance deduction % (0-100) |
| U_TotalAmount | decimal | 19,6 | Yes | Sum of all IPC lines |
| U_RetentionAmt | decimal | 19,6 | Yes | Calculated retention amount |
| U_AdvDeductAmt | decimal | 19,6 | No | Calculated advance deduction |
| U_NetPayable | decimal | 19,6 | Yes | Total - Retention - Adv Deduction |
| U_ARInvoiceNo | int | - | No | FK to OINV (generated invoice) |
| U_Remarks | nvarchar | 254 | No | Comments/notes |

# 3. IPC Calculation Logic

## 3.1 Formula Breakdown

| Calculation | Formula |
| --- | --- |
| Current Work Value | SUM(Contract Line Unit Price × Current Work Quantity) |
| Previous Work Value | SUM(All Previous IPCs Current Work Value for same Contract) |
| This IPC Work Value | Current Work Value - Previous Work Value |
| Retention Amount | This IPC Work Value × (Retention % ÷ 100) |
| Advance Deduction | This IPC Work Value × (Advance Deduction % ÷ 100) |
| Net Payable | This IPC Work Value - Retention Amount - Advance Deduction |

## 3.2 Calculation Example

| Item | Amount |
| --- | --- |
| Contract Total Value | $1,000,000.00 |
| Previous IPCs Total | $600,000.00 |
| Current Work Completed | $800,000.00 |
| This IPC Work Value | $200,000.00 |
| Less: Retention (10%) | ($20,000.00) |
| Less: Advance Deduction (5%) | ($10,000.00) |
| Net Payable to Contractor | $170,000.00 |

# 4. IPC Workflow States

| Status | Allowed Actions | Business Rules |
| --- | --- | --- |
| Draft | Edit, Submit, Delete | Can modify all fields. No invoice generated yet. |
| Submitted | Approve, Reject | Awaiting approval. Read-only for submitter. |
| Approved | Generate Invoice | Approved by authorized user. Ready for invoicing. |
| Rejected | Edit, Resubmit | Rejected by approver. Can be corrected and resubmitted. |
| Paid | View Only | Invoice generated and linked. Fully read-only. |

# 5. Integration with Contract Module

## 5.1 Data Synchronization

- When IPC is created, it inherits: Customer, Project, Currency, Retention %, Contract Line Items

- IPC status updates do not affect Contract status

- Contract tracks total IPCs generated and total amount invoiced

## 5.2 Validation Rules

- Cannot create IPC if Contract Status is Draft or Cancelled

- Current Work Completion % cannot exceed 100%

- Total of all IPCs cannot exceed Contract Value

- Cannot delete Contract if approved IPCs exist

# 6. A/R Invoice Generation

## 6.1 Automatic Invoice Creation

When IPC status changes to Approved, the system automatically generates an A/R Invoice in SAP B1 with the following mapping:

| IPC Field | A/R Invoice Field (OINV) |
| --- | --- |
| U_CustomerCode | CardCode (Customer) |
| U_IPCDate | DocDate (Document Date) |
| U_NetPayable | DocTotal (Invoice Total) |
| Code (IPC Number) | Comments / UDF Reference |
| Generated Invoice DocEntry | Stored back in U_ARInvoiceNo |

## 6.2 Invoice Line Items

Each IPC line becomes an invoice line with:

- Item Code (from Contract Line)

- Description: This IPC Work Value for Item

- Quantity: Current Work Qty - Previous Work Qty

- Unit Price: From Contract Line

- Line Total: Calculated from quantity × unit price

# 7. Standard IPC Reports

## 7.1 IPC Summary Report

Lists all IPCs with filters by Contract, Customer, Date Range, Status

- IPC Number, Contract Number, Customer Name

- IPC Date, Period From/To

- This IPC Value, Retention, Advance Deduction, Net Payable

- Status, Linked Invoice Number

## 7.2 Contract Payment History

Shows all IPCs for a specific contract

- IPC Number, Date, Period

- Current Work Value, Previous Work Value

- This IPC Work Value

- Retention & Advance Deduction Amounts

- Net Payable, Cumulative Payment

- Completion %: (Cumulative / Contract Total) × 100

End of IPC Module Specifications

Ready for Development